## Intro
Authority Approvals Processes
Emirate | Abbreviations |  |  | Other Abbreviations |  | Originator | Prerequisites
Dubai | DCAA | Dubai Civil Aviation Authority |  | TIS | Traffic Impact Study | Client | Affection Plan
| DCD | Dubai Civil Defense |  | DLTM | Dubai Local Transverse Mercator |  | Consultant Appointment Letters
| DDA | Dubai Development Authority |  | BP | Building Permit |  | Trade License /Passport and EID Copy
| DEWA | Dubai Electricity and Water Authority |  | DBPS | Dubai Building Permit System | Specialist | Topo Survey
| DM | Dubai Municipality |  | MEPS | Municipal Electronic Permitting System |  | Soil Investigation Report
| IACAD | Islamic Affairs and Charitable Activities Department |  | TS | Traffic Study | Master Developer | Gate Level
| KHDA | Knowledge and Human Development Authority |  | DLD | Dubai Land Department |  | Electrical Load Confirmation
| RTA | Roads and Transport Authority |  | NOI | Notice of Intent |  | Site Services Information
| EMPOWER | Emirates Central Cooling Systems Corporation |  | LDN | Load Demand Notification | RTA (Dubai) | Site Infra Information
| SIRA | Security Industry Regulatory Industry |  | WDN | Water Deamand Notification | MePS (Abu Dhabi & Al Ain) | Site Infra Information
| DS | Dubai South |  | SLD | Single Line Diagram | Authority | Plot Coordinates
| DTCM/DET | Dubai Economy and Tourism |  | MOI | Ministry of Interior |  | Max. Building Height
| DHA | Dubai Health Authority |  | BCC | Building Completion Certificate |  | Allowed GFA
| DSOA | Dubai Silicon Oasis |  | ROW | Right of Way |  | Land Use
Abu Dhabi | ADM | Abu Dhabi Municipality |  | EID | Emirates Identity Document |  | Accreditation Cards (Trakhees)
| ADSSC | Abu Dhabi Sewerage Services Company |  | ETS | Energy Transfer Station |  | Codes and Regulations
| ADCD | Abu Dhabi Civil Defense |  | NDA | Non-Disclosure Agreement |  | Setbacks
| ADDC | Abu Dhabi Distribution Company |  | COC | Certificate of Conformity |  | Plot Access
| ADWEA | Abu Dhabi Water and Electricity Authority |  | EHS | Environmental, Health and Safety |  | Application forms
| DCT | Department of Culture and Tourism |  | UPC | Urban Planning Council |  | Plot Area and Dimensions
| DOT | Department of Transport |  | EIA | Environmental Impact Assessment |  | Planning Information
| ITC | Integrated Transport Center |  | GB | Green Building |  | Parking Requirement
| EAD | Environmental Agency Abu Dhabi |  | GD | General Documents |  | Infra Tie-In Points
| ADAC | Abu Dhabi Airports Company |  | RERA | Real Estate Regulatory Authority | 3rd Party/House of Expertise (as applicable) | FLS
| MCC | Monitoring and Control center |  | SS | Substation |  | Structural Peer Review
Al Ain | AAM | Al Ain Municipality |  |  |  |  | Acoustics
| AACD | Al Ain Civil Defense |  |  |  |  | TIS
| AADC | Al Ain Distribution Company |  |  |  |  | SIRA
Sharjah | SM | Sharjah Municipality |  |  |  |  | Vertical Transportation
| SEWA | Sharjah Electricity and Water Authority |  |  |  |  | Swimming Pool
| SRTA | Sharjah Roads and Transport Authority |  |  |  |  | Infrastructure
| DTPS | Department of Town Planning and Survey
Authority | Useful Links: |  | Purpose:
DS | https://www.dubaisouth.ae/en/forms/planning-and-development |  | Guidelines, Regulations, Application Forms
Trakhees | https://trakhees.ae/en/Pages/Services.aspx |  | Guidelines, Regulations, Application Forms
DDA | https://gis.dda.gov.ae/portal/home/ |  | Plot Coordinates, Planning Information
| https://dda.gov.ae/dda-services/zoning-services/ |  | Application Requirements
RTA | https://www.rta.ae/wps/portal/rta/ae/home/rta-services |  | Application Requirements
ADSSC | https://www.adssc.ae/en-us/Media%20Center/Pages/Guidelines.aspx |  | Guidelines
| https://www.adssc.ae/en-us/Customer%20Service/Pages/Manuals_and_Procedures.aspx |  | Services Manual
DM | https://www.dm.gov.ae/ |  | DBC, Application Requirements
DM | https://www.makani.ae/desktop/?49 |  | Plot Information, Planning Information

## DM
Dubai Municipality Process and Requirements
Pre-Concept Stage | RTA | RTA Information NOC
1. Affection Plan 2. Consultant Appointment Letters 3. DEWA Undertaking Letter
| DM | Gate Level Request |  | DM | Auto TIS Assessment
Concept Stage | DM | Preliminary - New Building |  | DM | Request for Exceptions (if any)
| 1. Affection Plan 2. Architectural Drawings (DWF): 2.1 Cover Sheet 2.2 Drawings Schedule 2.3.Area Calculation Sheet 2.4 Site Setting Layout 2.5 Floor Plans 2.6 Elevations 2.7 Sections 2.8 Perspectives |  |  | 1. Applicable Drawings - Area for Exception to be clouded (DWF) 2. Valuation Certificate
Schematic Stage | BPCS DM Portal | DEWA NOC - Electricity |  | DM Planning Portal | Drainage Approval | IACAD | Islamic Affairs Approval (in case of Mosque)
| 1. Affection Plan 2. Site Setting Layout (DWF) 3. Project Details Sheet (DWF) |  |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. Project Details Sheet (DWF) |  | 1. Affection Plan 2. Architectural Drawings (PDF) 2.1 Cover Sheet 2.2 Drawings Schedule 2.3.Area Calculation Sheet 2.4 Site Setting Layout 2.5 Floor Plans 2.6 Elevations 2.7 Sections 2.8 Perspectives
| BPCS DM Portal | DEWA NOC - Water |  | SIRA | CCTV Approval
| 1. Affection Plan 2. Site Setting Layout (DWF) 3. Domestic Demand Calculation (DWF) |  |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. CCTV Layout (DWF)
| BPCS DM Portal | Telecom NOC - Etisalat
1. Affection Plan 2. Site Setting Layout (DWF) 3. Telecom Layout (DWF)
| BPCS DM Portal | FIC Approval
In same Application
Detailed Stage | DM | Final - New Building |  | BPCS DM Portal | DCD Approval | DEWA | Getting Electricity NOC
| 1. Affection Plan 2. Architectural Drawings (DWF): 2.1 Cover Sheet 2.2 Drawings Schedule 2.3.Area Calculation Sheet 2.4 Site Setting Layout 2.5 Floor Plans 2.6 Elevations 2.7 Sections 2.8 Perspectives 2.9 Wall Types, Sections & Details 2.10 Cladding Details 2.11 Stair Details 2.12 Lift Details 2.13 Door and Window Schedules 2.14 Boundary Wall Details 2.15 Wet Area Details 2.16 Service Room Details 2.17 Ramp Details 2.18 Accessibility Routes 2.19 Finishes Details 3. Mechanical Drawings (DWF) 3.1 Drawing Scehdule 3.2 General Notes 3.4 Standard Details 3.5 HVAC Setting Out Plan 3.6 HVAC Thermal Load Summary 3.7 HVAC Calculations and Data 3.8 HVAC Layouts 3.9 HVAC Riser Diagram 3.10 Drainage Setting Out Plan 3.11 Drainage Layouts 3.12 Drainage Schematics 3.13 Water Supply Setting Out Plan 3.14 Water Supply Layouts 3.15 Water Supply Schematics 4. Structure Drawings (DWF) 4.1 Drawing List 4.2 General Notes 4.3 Standard Details 4.4 Column Layouts 4.5 Foundation Details 4.6 Framing Details 4.7 Staircase Details 4.8 Core Wall Details 4.9 Water Tank Details 4.10 Compound Wall Details 5. SAFE and ETABS Calculations and Model |  |  | 1. Arch Life Safety (DWF) 2. Smoke Control (DWF) 3. Gas (DWF) 4. Fire Fighting and Fire Protection (DWF) 5. Fire Alarm and Emergency Lighting (DWF) |  | 1. Project summary of total connected load-max demand schedule 2. MDB/SMDB Load Schedule 3. Singe Line Diagram with proposed LV distribution and tariff metering 4. Site Setting layout and ground floor plan indicating location of substation, LV room (Along with dimensional details of LV room , arrangements of LV panels, MDBs , kWh meter etc.). 5. Ground floor and or /Typical floor layout indicating of electrical rooms/MBD/SMDM/DB, etc.) 6-Terms and Conditions Form
|  |  |  | BPCS DM Portal | RTA Preliminary Design Approval | DEWA | Getting Water NOC
|  |  |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. Plot Access and Curb Cut (DWF) |  | 1. Premise Details Sheet 2. Detailed Description Schedule for Meters 3. Ground Floor/Roof Plan with Water Meter Arrangement 4. Site Setting layout and ground floor 5. Tapping Point Pictures
Enabling Works Approvals and NOC's
| DM | Fencing Permit Application
| DM | Preliminary Arrangement and Digging
| DM | Final Arrangement and Digging
Other Applications - as applicable
| DM | Modification/Adjustment Approval
Arch/STR/MECH - As Approved/As Revised Drawings
| BPCS DM Portal | DCD Revision |  | BPCS DM Portal | DEWA Water - Building NOC | BPCS DM Portal | DEWA Electricity - Building NOC
|  |  |  | BPCS DM Portal | Telecom NOC | BPCS DM Portal | Drainage Revision
| DM | Modification/Adjustment Permit

## DDA
Dubai Development Authority Process and Requirements
Pre-Concept Stage | RTA | RTA Information NOC
1. Affection Plan 2. Consultant Appointment Letters 3. DEWA Undertaking Letter
| Master Developer | Gate Level Request
1. Affection Plan 2. Consultant Appointment Letter 3. Cover Letter
| Master Developer | Site Services Information | EMPOWER | ETS Room NOI (if applicable) | Master Developer | Electrical Load Confirmation
| 1. Affection Plan 2. Consultant Appointment Letter 3. Cover Letter |  | 1. Affection Plan 2. Consultant Appointment Letter 3. Cover Letter 4. Application Form for District Cooling Service |  | 1. Affection Plan 2. Consultant Appointment Letter 3. Cover Letter
Concept Stage | DDA | Zoning Exceptions (if applicable)
1. Affection Plan 2. Cover Letter 3. Arch Drawings (PDF)
| DDA | Land Demarcation | DDA | Soil Report Review | DCAA | Building Height NOC
| 1. Affection Plan 2. Consultant Appointment Letter |  | 1. Affection Plan 2. Soil Report 3. Detailed Geotechnical Calculations 4. Accrediation Certificate from EIAC 5. Borehole Drawings (DWF) |  | 1-Affection Plan (PDF) 2-Perspectives (JPG) 3-Elevations (PDF)
| DDA | Preliminary Design | RTA | Studying Access Design NOC | RTA | TIS (if required - to be done by specialist)
| 1. Affection Plan 2. Architectural Drawings (DWF): 2.1 Cover Sheet 2.2 Project Documents Sheet 2.3 Drawings Schedule 2.4.Area Calculation Sheet 2.5 Site Setting Layout 2.6 Floor Plans 2.7 Elevations 2.8 Sections 2.9 Perspectives 3. Consultant Appointment Letter 4. Gate Level Approval 5. IACAD Approval (if applicable) |  | 1. Affection Plan 1. Affection Plan 2. Site Setting Layout (PDF) 3. Plot Access and Curb Cut (PDF) 5. Site Photos (PDF) |  | 1. Traffic Analysis for Access Points 2. Parking Demand and Supply Calculations 3. Parking Layouts of Basement/Ground Floor and other levels 4. Traffic Circulation Plan for the Development 5. Concept Access Layout
Schematic Stage | DEWA | Building NOC - Electricity | DEWA | Building NOC - Water | RTA | RTA Preliminary Design Approval
| 1. Affection Plan 2. Site Setting Layout (DWF) 3. Project Details Sheet (DWF) |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. Domestic Demand Calculation (DWF) |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. Plot Access and Curb Cut (DWF)
| Etisalat/DU | Telecom NOC - Etisalat | Master Developer | Sewerage Connection Confirmation | SIRA | CCTV Approval
| 1. Affection Plan 2. Site Setting Layout (DWF) 3. Telecom Layout (DWF) |  | 1. Affection Plan 2. Consultant Appointment Letter 3. Cover Letter 4. Project Details Form 5. Sewerage Calculations |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. CCTV Layout (DWF)
| DM Planning Portal | Swimming Pool Approval (if applicable) | DCD | DCD Approval | EMPOWER | ETS Room NOC (if applicable)
| 1. Swimming Pool Drawings (DWF) 1.1 Cover Sheet with Owners Signature 1.2 Project Documents Sheet 1.3 Setting Out Plan 1.4 Swimming Pool Details Plan 1.5 Section 1.6 Pipe Fitting Layout 1.7 Pool and Pump Electricity Diagram 1.8 Schematic Diagram 1.9 Drainage Schematic 1.10 Pump Room Layout 1.11 Equipment Details |  | 1. Arch Life Safety (PDF) 2. Smoke Control (PDF) 3. Gas (PDF) 4. Fire Fighting and Fire Protection (PDF) 5. Fire Alarm and Emergency Lighting (PDF) |  | 1. Affection Plan 2. NDA's signed all Parties 3. Cover Letter 4. Confirmation of Acceptance of EMPOWERS Rates and Charges 5. Land Sales Agreement/SPA 6. Passport, Visa & Emirates ID of Owner / Trade License for company 7. VAT Registration Certificate for company 8. Letter of Confirmation fo the Demand Load & Delivery Date 9. Setting Out Plan (PDF and DWG) 10. Building plan showing location of ETS room along with plot limit & its DLTM coordinates (PDF & DWG) 11. An enlarged ETS room layout showing the clear dimensions of the room and door height. (PDF & DWG) 12. ETS room cross section details which inclusive of Beam / Floor slab or any level changes (PDF & DWG) 13. Proposed chilled water pipe routing details from the plot limit to ETS room (PDF & DWG) 14. If the building does not have any basement pit / trench details for chilled water pipe entry (PDF & DWG) 15. Chilled water pipe routing from the building entry point towards the ETS room (PDF & DWG) 16. Chilled Water Schematic Riser Diagram showing the structural level of each floor of the building (PDF & DWG) 17. Proposed Chilled water pipe entry and its cross section details (PDF & DWG)
Detailed Stage | DDA | Detailed Design Approval
1. Affection Plan 2. Architectural Drawings (DWF): 2.1 Cover Sheet 2.2 Drawings Schedule 2.3 Project Document Sheet 2.4.Area Calculation Sheet 2.5 Site Setting Layout 2.6 Floor Plans 2.7 Elevations 2.8 Sections 2.9 Perspectives 2.10 Wall Types, Sections & Details 2.11 Cladding Details 2.12 Stair Details 2.13 Lift Details 2.14 Door and Window Schedules 2.15 Boundary Wall Details 2.16 Wet Area Details 2.17 Service Room Details 2.18 Ramp Details 2.19 Accessibility Routes 2.20 Finishes Details 3. Mechanical Drawings (DWF) 3.1 Drawing Scehdule 3.2 General Notes 3.4 Standard Details 3.5 HVAC Setting Out Plan 3.6 HVAC Thermal Load Summary 3.7 HVAC Calculations and Data 3.8 HVAC Layouts 3.9 HVAC Riser Diagram 3.10 Drainage Setting Out Plan 3.11 Drainage Layouts 3.12 Drainage Schematics 3.13 Water Supply Setting Out Plan 3.14 Water Supply Layouts 3.15 Water Supply Schematics 4. Structure Drawings (DWF) 4.1 Drawing List 4.2 General Notes 4.3 Standard Details 4.4 Column Layouts 4.5 Foundation Details 4.6 Framing Details 4.7 Staircase Details 4.8 Core Wall Details 4.9 Water Tank Details 4.10 Compound Wall Details 5. SAFE and ETABS Calculations and Model 6. Gate Level Approval 7. Sewerage Connection Approval from Master Developer 8. SIRA Approval 9. IACAD Approval (if applicable) 10. DCD Approval 11. Swimming Pool Approval (if applicable) 12. EMPOWER Approval (if applicable) 13. DCAA NOC (if applicable) 14. Greenbuilding Cheklist 15. Project Calculations Sheet 13. Telecom NOC 14. DEWA NOC 15. Mechanical Checklist 16. Structural Checklist 17. TIS Approval (if applicable)
Construction Stage | DDA | Building Permit | DEWA | Getting Electricity NOC
| *Application submitted by Contractor |  | 1. Project summary of total connected load-max demand schedule 2. MDB/SMDB Load Schedule 3. Singe Line Diagram with proposed LV distribution and tariff metering 4. Site Setting layout and ground floor plan indicating location of substation, LV room (Along with dimensional details of LV room , arrangements of LV panels, MDBs , kWh meter etc.). 5. Ground floor and or /Typical floor layout indicating of electrical rooms/MBD/SMDM/DB, etc.) 6-Terms and Conditions Form
| DDA | Post-Tension Design Approval | DEWA | Getting Water NOC
| 1-Approved Elevation Drawings 2-Proposed Podium Treatment Drawings 3-Official Request Letter 4- Applicable Drawings |  | 1. Premise Details Sheet 2. Detailed Description Schedule for Meters 3. Ground Floor/Roof Plan with Water Meter Arrangement 4. Site Setting layout and ground floor 5. Tapping Point Pictures
| DDA | Podium Treatment/Material Approval (if applicable)
1-Copy of Specialist Contractor's Trade License 2-Approved relevant Structural Drawings 3-Structural Design Drawings 4-Structural Calculations and Models 5-Post Tension Design review Checklist
Applications by Contractor as applicable
| DDA | Soil Investigation Inspection
| DDA | Excavation Permit | DDA | Piling Permit
| DDA | 3rd Party Building Survey Review | DDA | Piling Inspection
| DDA | Final Land Demarcation | DDA | Piling Completion Certificate
| DDA | Inspection for Final Building Completion
| DDA | Building completion Certificate

## Trakhees
Trakhees Process and Requirements
Pre-Concept Stage | Nakheel | Electrical Load Confirmation Letter 1
1. Affection Plan 2. Cover Letter 3. Consutant Appointment Letter for Nakheel
| Nakheel | Infrastructure Plot Details Information 2 | Trakhees | Project Registration 3
| 1. Affection Plan 2. Topo Survey 3. Consutant Appointment Letter for Nakheel |  | 1. Consultant Appointment Letter to Trakhees 2. Engineering Practice Certificate 3. Consultant Trade License 4. Affection Plan 5. Cover Letter to Trakhees 6. Owner Trade License/Emirates ID
| Nakheel | Initial Demarcation 4 | EMPOWER | ETS Room NOI (if applicable) 5
| 1. Affection Plan 2. Consultant Trade License 3. Topo Survey |  | 1. Affection Plan 2. Consultant Appointment Letter 3. Cover Letter 4. Application Form for District Cooling Service
Concept Stage | Nakheel | Preliminary Design 6 | Nakheel | Exceptions NOC (if applicable) 7 | DCAA | Building Height NOC 8
| 1. Affection Plan 2. Consultant Trade License 3. Consultant Appointment Letter for Nakheel 4. Client Passport Copy/Trade License 5. Combined CAD Drawing 6. Cover Sheet 7. Road Layout and Levels (Topo Survey) 8. Parking Calculation 9. Setting Layout Plan 10. Boundary Wall Details 11. Infra Drawings 12. Initial Demarcation Certificate 13. -Combined PDF 14. Swimming Pool Undertaking Letter - signed and stamped |  | 1. Affection Plan 2. Cover Letter with details of Exceptions 3. Consultant Trade License 4. Consultant Appointment Letter 5. Owner's Passport Copy or EID 6. Undertaking for Exception |  | 1-Affection Plan (PDF) 2-Perspectives (JPG) 3-Elevations (PDF)
| Nakheel | Plot Access and Curb Cut NOC 9
1. Cover Letter 2. Plot Access and Curb Cut Drawing PDF and CAD 3. Consultant Appointment Letter 4. Trade License 5. Affection Plan 6. Nakheel Preliminary Design Approval 7. Topo survey 8. Undertaking Letter for Plot Access/Curb Cut for Nakheel
| RTA | Studying Design Access NOC 10 | RTA | TIS (if required - to be done by specialist) 11
| 1. Affection Plan 2. Plot Access and Curb Cut NOC 3. Plot Access and Curb Cut Drawing (PDF) 5. Site Photos (PDF) |  | 1. Traffic Analysis for Access Points 2. Parking Demand and Supply Calculations 3. Parking Layouts of Basement/Ground Floor and other levels 4. Traffic Circulation Plan for the Development 5. Concept Access Layout
| Trakhees | Concept Design 12 | Trakhees | Exceptions NOC (if applicable) 13
| 1. GD - Consultants Documents (All Accreditation Cards; Consultant Appointment Letter for Trakhees; Trade License; DM Practice Certificate; Cover Letter for Trakhees) 2. GD - Client Documents (Trade License; Passport Copy) 3. GD - Affection Plan 4. GD - Application Form 5. GD - All Approved NOC's (DEWA/Telecom/Demarcation/DCD) 6. GD - Architecture Verfification List (Trakhees Template) 7. GD - Approved Nakheel Concept Design 8. ARCH - Architectural Drawings PDF and CAD 9. ARCH - Area Calculation Sheet (DWF) 10. ARCH - Verification Checklist |  | 1. GD - Demarcation Certificate 2. GD - Cover Letter 3. GD - Approved Trakhees PD 4. GD - Application Form (Exceptions NOC) 5. GD - Consultant Docs (Accreditation Cards, Trade License, Consultant Appointment Letter, DM Practice Certificate) 6. GD - Contractor Docs (Accreditation Cards, Trade License, Contractor Appointment Letter, DM Practice Certificate) 7. GD - Affection Plan 8. GD - Nakheel NOC 9. GD - Cover Letter with details of Exceptions to Trakhees 10. Undertaking for Exception (Area Increment) to Trakhees 11. ARCH - Drawings
Schematic Stage | DEWA | Building NOC - Electricity 14 | DEWA | Building NOC - Water 15
| 1. Affection Plan 2. Site Setting Layout (DWF) 3. Project Details Sheet (DWF) |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. Domestic Demand Calculation (DWF)
| Etisalat/DU | Telecom NOC 16 | Nakheel | Sewerage Design NOC 17 | SIRA | CCTV Approval 18
| 1. Affection Plan 2. Site Setting Layout (DWF) 3. Telecom Layout (DWF) |  | 1. Consultant Trade License 2. Affection Plan 3. Swimming Pool Undertaking Letter from Client 4. Sewerage Design Drawings (CAD and PDF) 5. Nakheel Infrastructure Drawings |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. CCTV Layout (DWF)
| DCD | DCD Approval 19 | EMPOWER | ETS Room NOC 20
| 1. Arch Life Safety (PDF) 2. Smoke Control (PDF) 3. Gas (PDF) 4. Fire Fighting and Fire Protection (PDF) 5. Fire Alarm and Emergency Lighting (PDF) |  | 1. Affection Plan 2. NDA's signed all Parties 3. Cover Letter 4. Confirmation of Acceptance of EMPOWERS Rates and Charges 5. Land Sales Agreement/SPA 6. Passport, Visa & Emirates ID of Owner / Trade License for company 7. VAT Registration Certificate for company 8. Letter of Confirmation fo the Demand Load & Delivery Date 9. Setting Out Plan (PDF and DWG) 10. Building plan showing location of ETS room along with plot limit & its DLTM coordinates (PDF & DWG) 11. An enlarged ETS room layout showing the clear dimensions of the room and door height. (PDF & DWG) 12. ETS room cross section details which inclusive of Beam / Floor slab or any level changes (PDF & DWG) 13. Proposed chilled water pipe routing details from the plot limit to ETS room (PDF & DWG) 14. If the building does not have any basement pit / trench details for chilled water pipe entry (PDF & DWG) 15. Chilled water pipe routing from the building entry point towards the ETS room (PDF & DWG) 16. Chilled Water Schematic Riser Diagram showing the structural level of each floor of the building (PDF & DWG) 17. Proposed Chilled water pipe entry and its cross section details (PDF & DWG)
Detailed Stage | Nakheel | Final Design Design 21
1. Cover Letter 2. Consultant Trade License 3. Affection Plan 4. Consultant Appointment Letter 5. Owners Passport Copy/Trade License 6. Combined CAD Drawings 7. Cover Sheet 8. Parking Calculation 9. BUA and GFA Calculation 10. Setting Layout Plan 11. Road Layout and Levels (Topo Survey) 12. Longitudnal and Cross Sections 13. Boundary Wall Details 14. Infra Drawings 15. Demarcation Certificate 16. Combined PDF 17. Sewerage NOC 18. Plot Access/Curb Cut NOC 19. Trakhees PD NOC and Stamped Drawings 20. Utilities NOC 21. Nakhee lPreliminary Approval NOC
| Trakhees | Building Permit 22
1. GD - Cover Letter and Application Form 2. GD - Approved Trakhees PD 3. GD - Approved Nakheel FD 4. GD - Approved Nakheel PD 5. GD - Consultant Docs (Accreditation Cards, Trade License, Consultant Appointment Letter, DM 7-Practice Certificate) 6. GD - Contractor Docs (Accreditation Cards, Trade License, Contractor Appointment Letter, DM Practice Certificate) 7. GD - NOC's (DEWA, Etisalat DCD, RTA) 8. GD - Affection Plan 9. GD - Architectural Verification Checklist 10. HVAC - Drawings and HAP Calcs 11. HVAC - HVAC Checklist 12. ARCH - Arch Drawings 13. ARCH - Area Calculation Sheet 14. EHS - Drainage Drawings & Details 16.EHS - EHS Submission Booklet 17. EHS - Copy of Payment 18. EHS - Undertaking Letters from Client 19. STR - Design Calculations 20. STR - Soil Investigation Report 21. STR - Structural Drawings
Construction Stage | DEWA | Getting Electricity NOC 23 | Nakheel | Mobilization - Site Access 24 | Trakhees | Mobilization & Signboard 25
| 1. Project summary of total connected load-max demand schedule 2. MDB/SMDB Load Schedule 3. Singe Line Diagram with proposed LV distribution and tariff metering 4. Site Setting layout and ground floor plan indicating location of substation, LV room (Along with dimensional details of LV room , arrangements of LV panels, MDBs , kWh meter etc.). 5. Ground floor and or /Typical floor layout indicating of electrical rooms/MBD/SMDM/DB, etc.) 6-Terms and Conditions Form |  | 1. Authorization Letter from Owner 2. Affection Plan 3. Trakhees Approval of Mobilization and Signboard 4. Copy of Consruction Security Cheque from Owner *To be applied by Contractor/Owner |  | 1. GD - Cover Letter 2. GD - Application Form 3. GD- Consultant Docs (Accreditation Cards, Trade License, Consultant Appointment Letter, DM Practice Certificate) 4. GD - Specialist Contractor Docs (Accreditation Cards, Trade License, Contractor Appointment Letter, DM Practice Certificate) 5. GD - Affection Plan 6. STR - Fence Drawings and Details
| DEWA | Getting Water NOC 26 | DM | Advertising Permit 27 | Trakhees | Soil Investigation NOC 28
| 1. Premise Details Sheet 2. Detailed Description Schedule for Meters 3. Ground Floor/Roof Plan with Water Meter Arrangement 4. Site Setting layout and ground floor 5. Tapping Point Pictures |  | 1. Hoarding Drawings 2. Nakheel Mobilization - Site Access NOC 3. Cover Letter 4. Affection Plan 5. Adverts/Banner Design *To be applied by Owner |  | 1. Application Form 2. Specialist Trade License 3. Specialist Appointment Letter 4. Soil Report 5. Borehole Drawings
Applications by Contractor as applicable
| Trakhees | Initial Demarcation NOC
| Trakhees | Shoring/Piling NOC (if required) | Nakheel | Dewatering NOC (if required)
| Trakhees | Structural Inspections | Nakheel | Dewatering NOC (if required)
| Trakhees | Sustainability Site Report | Trakhees | Redemarcation NOC
| Trakhees | Final Inspections
| Trakhees | Building Completion Certificate

## DS
Dubai South Process and Requirements
Pre-Concept Stage | DS | Site Services Information Request 1 | RTA | RTA Information NOC 2
| 1. Affection Plan 2. Consultant Trade License 3. Cover Letter 4. Application Form |  | 1. Affection Plan 2. Consultant Appointment Letters 3. DEWA Undertaking Letter
Concept Stage | DS | Preliminary Design 3 | DS | Soil Investigation Request 4 | RTA | Studying Access Design NOC 5
| 1. Affection Plan 2. Architectural Drawings (DWF): 2.1 Cover Sheet 2.2 Project Documents Sheet 2.3 Drawings Schedule 2.4.Area Calculation Sheet 2.5 Site Setting Layout 2.6 Floor Plans 2.7 Elevations 2.8 Sections 2.9 Perspectives 3. Consultant Appointment Letter 4. Application Form |  | 1. Affection Plan 2. Soil Report 3. Detailed Geotechnical Calculations 4. Accrediation Certificate from EIAC 5. Borehole Drawings (PDF) 6. Consultant Dubai South Registration 7. Application Form |  | 1. Affection Plan 1. Affection Plan 2. Site Setting Layout (PDF) 3. Plot Access and Curb Cut (PDF) 5. Site Photos (PDF)
Schematic Stage | DEWA | Building NOC - Electricity 6 | DEWA | Building NOC - Water 7
| 1. Affection Plan 2. Site Setting Layout (DWF) 3. Project Details Sheet (DWF) |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. Domestic Demand Calculation (DWF)
| Etisalat/DU | Telecom NOC 8 | DS | Sewerage and Drainage Approval 9
| 1. Affection Plan 2. Site Setting Layout (DWF) 3. Telecom Layout (DWF) |  | 1. Affection Plan 2. Sewerage Design Drawings (CAD and PDF) 3. Application Form 4. Consultant DS Registration
| SIRA | CCTV Approval 10 | DS | District Cooling Approval 11
| 1. Affection Plan 2. Site Setting Layout (DWF) 3. CCTV Layout (DWF) |  | 1. Affection Plan 2. ETS Room Drawings (CAD and PDF) 3. Application Form 4. Consultant DS Registration
| DCD | DCD Approval 12
1. Arch Life Safety (PDF) 2. Smoke Control (PDF) 3. Gas (PDF) 4. Fire Fighting and Fire Protection (PDF) 5. Fire Alarm and Emergency Lighting (PDF)
Detailed Stage | DS | Detailed Design Approval 13
1. Affection Plan 2. Architectural Drawings (DWF): 2.1 Cover Sheet 2.2 Drawings Schedule 2.3 Project Document Sheet 2.4.Area Calculation Sheet 2.5 Site Setting Layout 2.6 Floor Plans 2.7 Elevations 2.8 Sections 2.9 Perspectives 2.10 Wall Types, Sections & Details 2.11 Cladding Details 2.12 Stair Details 2.13 Lift Details 2.14 Door and Window Schedules 2.15 Boundary Wall Details 2.16 Wet Area Details 2.17 Service Room Details 2.18 Ramp Details 2.19 Accessibility Routes 2.20 Finishes Details 3. Structure Drawings (DWF) 3.1 Drawing List 3.2 General Notes 3.3 Standard Details 3.4 Column Layouts 3.5 Foundation Details 3.6 Framing Details 3.7 Staircase Details 3.8 Core Wall Details 3.9 Water Tank Details 3.10 Compound Wall Details 4. SAFE and ETABS Calculations and Model 5. RTA Approval 7. Sewerageand Drainage Approval 8. SIRA Approval 9. IACAD Approval (if applicable) 10. DCD Approval 11. Swimming Pool Approval (if applicable) 12. District Cooling Approval (if applicable) 13. Telecom NOC 14. DEWA NOC
Construction Stage | Applications by Contractor as applicable
| DS | Land Demarcation | DS | Enabling Works | DS | Mobilization
[5 empty] | DS | HSE NOC for BP
[5 empty] | DS | Building Permit
|  |  | DS | HSE NOC for BCC | DS | Structural Inspections
|  |  | DS | Building Completion Certificate

## DSOA
Dubai Silicon Oasis Authority (DSOA) / DIEZ Process and Requirements
Pre-Concept Stage | RTA | RTA Information NOC 1
1. Affection Plan 2. Consultant Appointment Letters 3. DEWA Undertaking Letter
| DSOA | Gate Level Request 2
1. Affection Plan 2. Consultant Appointment Letter 3. Cover Letter
| DSOA | Site Services Information 3 | DSOA | Electrical Load Confirmation 4
| 1. Affection Plan 2. Consultant Appointment Letter 3. Cover Letter |  | 1. Affection Plan 2. Consultant Appointment Letter 3. Cover Letter
Concept Stage | DSOA | Exceptions 5
1. Affection Plan 2. Cover Letter 3. Arch Drawings (PDF)
| DSOA | Land Demarcation 6 | DSOA | Soil Report Review 7 | DCAA | Building Height NOC 8
| 1. Affection Plan 2. Consultant Appointment Letter |  | 1. Affection Plan 2. Soil Report 3. Detailed Geotechnical Calculations 4. Accrediation Certificate from EIAC 5. Borehole Drawings (DWF) |  | 1-Affection Plan (PDF) 2-Perspectives (JPG) 3-Elevations (PDF)
| DSOA | Preliminary Design 9 | RTA | Studying Access Design NOC 10 | RTA | TIS (if required - to be done by specialist) 11
| 1. Affection Plan 2. Architectural Drawings (DWF): 2.1 Cover Sheet 2.2 Project Documents Sheet 2.3 Drawings Schedule 2.4.Area Calculation Sheet 2.5 Site Setting Layout 2.6 Floor Plans 2.7 Elevations 2.8 Sections 2.9 Perspectives 3. Consultant Appointment Letter 4. Gate Level Approval 5. IACAD Approval (if applicable) |  | 1. Affection Plan 1. Affection Plan 2. Site Setting Layout (PDF) 3. Plot Access and Curb Cut (PDF) 5. Site Photos (PDF) |  | 1. Traffic Analysis for Access Points 2. Parking Demand and Supply Calculations 3. Parking Layouts of Basement/Ground Floor and other levels 4. Traffic Circulation Plan for the Development 5. Concept Access Layout
Schematic Stage | DEWA | Building NOC - Electricity 12 | DEWA | Building NOC - Water 13 | RTA | RTA Preliminary Design Approval 14
| 1. Affection Plan 2. Site Setting Layout (DWF) 3. Project Details Sheet (DWF) |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. Domestic Demand Calculation (DWF) |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. Plot Access and Curb Cut (DWF)
| Etisalat/DU | Telecom NOC - Etisalat 15 | DSOA | Sewerage Connection Confirmation 16 | SIRA | CCTV Approval 17
| 1. Affection Plan 2. Site Setting Layout (DWF) 3. Telecom Layout (DWF) |  | 1. Affection Plan 2. Consultant Appointment Letter 3. Cover Letter 4. Project Details Form 5. Sewerage Calculations |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. CCTV Layout (DWF)
| DCD | DCD Approval 18
1. Arch Life Safety (PDF) 2. Smoke Control (PDF) 3. Gas (PDF) 4. Fire Fighting and Fire Protection (PDF) 5. Fire Alarm and Emergency Lighting (PDF)
Detailed Stage | DM | Final - New Building 19
1. Affection Plan 2. Architectural Drawings (DWF): 2.1 Cover Sheet 2.2 Drawings Schedule 2.3.Area Calculation Sheet 2.4 Site Setting Layout 2.5 Floor Plans 2.6 Elevations 2.7 Sections 2.8 Perspectives 2.9 Wall Types, Sections & Details 2.10 Cladding Details 2.11 Stair Details 2.12 Lift Details 2.13 Door and Window Schedules 2.14 Boundary Wall Details 2.15 Wet Area Details 2.16 Service Room Details 2.17 Ramp Details 2.18 Accessibility Routes 2.19 Finishes Details 3. Mechanical Drawings (DWF) 3.1 Drawing Scehdule 3.2 General Notes 3.4 Standard Details 3.5 HVAC Setting Out Plan 3.6 HVAC Thermal Load Summary 3.7 HVAC Calculations and Data 3.8 HVAC Layouts 3.9 HVAC Riser Diagram 3.10 Drainage Setting Out Plan 3.11 Drainage Layouts 3.12 Drainage Schematics 3.13 Water Supply Setting Out Plan 3.14 Water Supply Layouts 3.15 Water Supply Schematics 4. Structure Drawings (DWF) 4.1 Drawing List 4.2 General Notes 4.3 Standard Details 4.4 Column Layouts 4.5 Foundation Details 4.6 Framing Details 4.7 Staircase Details 4.8 Core Wall Details 4.9 Water Tank Details 4.10 Compound Wall Details 5. SAFE and ETABS Calculations and Model

## EMPOWER
EMPOWER Process and Requirements
Pre-Concept Stage | EMPOWER | ETS Room NOI
1. Affection Plan 2. Consultant Appointment Letter 3. Cover Letter 4. Application Form for District Cooling Service
Schematic Stage | EMPOWER | ETS Room NOC
1. Affection Plan 2. NDA's signed all Parties 3. Cover Letter 4. Confirmation of Acceptance of EMPOWERS Rates and Charges 5. Land Sales Agreement/SPA 6. Passport, Visa & Emirates ID of Owner / Trade License for company 7. VAT Registration Certificate for company 8. Letter of Confirmation fo the Demand Load & Delivery Date 9. Setting Out Plan (PDF and DWG) 10. Building plan showing location of ETS room along with plot limit & its DLTM coordinates (PDF & DWG) 11. An enlarged ETS room layout showing the clear dimensions of the room and door height. (PDF & DWG) 12. ETS room cross section details which inclusive of Beam / Floor slab or any level changes (PDF & DWG) 13. Proposed chilled water pipe routing details from the plot limit to ETS room (PDF & DWG) 14. If the building does not have any basement pit / trench details for chilled water pipe entry (PDF & DWG) 15. Chilled water pipe routing from the building entry point towards the ETS room (PDF & DWG) 16. Chilled Water Schematic Riser Diagram showing the structural level of each floor of the building (PDF & DWG) 17. Proposed Chilled water pipe entry and its cross section details (PDF & DWG)

## DEWA
DEWA Process and Requirements
Schematic Stage | DEWA | Building NOC - Electricity 1 | DEWA | Building NOC - Water 2
| 1. Affection Plan 2. Site Setting Layout (DWF) 3. Project Details Sheet (DWF) |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. Domestic Demand Calculation (DWF)
Construction Stage | DEWA | Getting Electricity NOC 3
1. Project summary of total connected load-max demand schedule 2. MDB/SMDB Load Schedule 3. Singe Line Diagram with proposed LV distribution and tariff metering 4. Site Setting layout and ground floor plan indicating location of substation, LV room (Along with dimensional details of LV room , arrangements of LV panels, MDBs , kWh meter etc.). 5. Ground floor and or /Typical floor layout indicating of electrical rooms/MBD/SMDM/DB, etc.) 6-Terms and Conditions Form
| DEWA | Getting Water NOC 4
1. Premise Details Sheet 2. Detailed Description Schedule for Meters 3. Ground Floor/Roof Plan with Water Meter Arrangement 4. Site Setting layout and ground floor 5. Tapping Point Pictures

## RTA
RTA Process and Requirements
Pre-Concept Stage | RTA | RTA Information NOC 1
1. Affection Plan 2. Consultant Appointment Letters 3. DEWA Undertaking Letter
Concept Stage | RTA ROWPS | Studying Access Design NOC 2
1. Affection Plan 2. Site Setting Layout (PDF) 3. Plot Access and Curb Cut (PDF) 5. Site Photos (PDF)
Schematic Stage | RTA ENOC | TIS (if required - to be done by specialist) 3
1. Traffic Analysis for Access Points 2. Parking Demand and Supply Calculations 3. Parking Layouts of Basement/Ground Floor and other levels 4. Traffic Circulation Plan for the Development 5. Concept Access Layout
| RTA ENOC | RTA Preliminary Design Approval 4
1. Affection Plan 2. Site Setting Layout (DWF) 3. Plot Access and Curb Cut (DWF)
Detailed Stage | RTA ENOC | Final Design Approval 5
1. Affection Plan 2. Site Setting Layout (DWF) 3. Plot Access and Curb Cut (DWF) 4. Other Approved Layouts

## IACAD
Islamic Affairs and Charitable Affairs Department Process and Requirements
Concept Stage | IACAD | Concept Design Approval 1
1. Affection Plan 2. Consultant Appointment Letter 3. Architectural Drawings (PDF and CAD): 3.1 Cover Sheet 3.2 Project Documents Sheet 3.3 Drawings Schedule 3.4.Area Calculation Sheet 3.5 Site Setting Layout 3.6 Floor Plans 3.7 Elevations 3.8 Sections 3.9 Perspectives
Detailed Stage | IACAD | Detailed Design Approval
1. Affection Plan 2. Architectural Drawings (PDF and CAD): 2.1 Cover Sheet 2.2 Drawings Schedule 2.3 Project Document Sheet 2.4.Area Calculation Sheet 2.5 Site Setting Layout 2.6 Floor Plans 2.7 Elevations 2.8 Sections 2.9 Perspectives 2.10 Wall Types, Sections & Details 2.11 Cladding Details 2.12 Stair Details 2.13 Lift Details 2.14 Door and Window Schedules 2.15 Boundary Wall Details 2.16 Wet Area Details 2.17 Service Room Details 2.18 Ramp Details 2.19 Accessibility Routes 2.20 Finishes Details

## DCD
Dubai Civil Defense Process and Requirements
Detailed Stage | DCD | DCD Approval 1
1. Arch Life Safety (PDF) 2. Smoke Control (PDF) 3. Gas (PDF) 4. Fire Fighting and Fire Protection (PDF) 5. Fire Alarm and Emergency Lighting (PDF)
Construction Stage | DCD | Modification Approval (as required) 2
As Approved As Revised Drawings (Clouded PDF) - as applicable: 1. Arch Life Safety (PDF) 2. Smoke Control (PDF) 3. Gas (PDF) 4. Fire Fighting and Fire Protection (PDF) 5. Fire Alarm and Emergency Lighting (PDF) 6. List of Changes (Letter - PDF)

## DCAA
Dubai Civil Aviation Authority Process and Requirements
Concept Stage | DCAA | Building Height NOC
1-Affection Plan (PDF) 2-Perspectives (JPG) 3-Elevations (PDF)
Schamtic Stage | DCAA | Aircraft Warning Light NOC
1. Light Type (Intensity Type) 2. Beam Coverage (Clockwise Direction) 3. Light Elevation (Meters above Ground Level) 4. Structure Location (Geographical Coordinates)

## ADM
Abu Dhabi Municipality Process and Requirements
Pre-Concept Stage | SmartHub | Plot Setting Out Study (If applicable) 1 | MEPS | Project Registration 2
| 1. Affection Plan 2. Owner's ID/Trade License 3. Consultant Appointment Letter 4. Authorization & Undertaking Form |  | 1. Affection Plan / Site Plan 2. Owner's ID/Trade License 3. Consultant Appointment Authorization & Undertaking Form 4. Owner Approval Form for Project Registration
|  |  | MEPS | Site Approval and Clearances 3
1. Affection Plan / Site Plan 2. Owner's ID/Trade License 3. Consultant Appointment Authorization & Undertaking Form 4. Site Approval and Clearances Form 6. Owner Approval Form for Project Registration
|  |  | ADSSC | NOI - Request for GIS Information (If applicable) 4
1. Affection Plan 2. Owner's ID/Trade License 3. Consultant Appointment Letter
Concept Stage | ITC | TIS (if required - applied by Specialist) 5 | ADM | Exceptions Approval (if required) 6 | MEPS | Soil Investigation Work Permit 7
| 1. Affection Plan 2. Site Traffic Generation 3. Traffic Access and Circulation Plans 4. Site Access Review 5. Public Transit and Non-Motorized Plans 5. Parkign Study 6. TIS Summary Plans |  | 1. Affection Plan 2. Architectural Drawings (PDF): 2.1 Plans, Sections, Elevations highlighting area for Exception 3. Variety request form (filled & signed). |  | 1. Authorization and Undertaking Letter for Soil Test Permit 2. Certified Site Plan 3. Contractor Assignment Letter 4. Employee List for the Laboratory 5. ENAS accreditation certificate from Emirates Authority For Standardization and Metrology 6. Final Demarcation 7. General layout indicating borehole locations and coordinates stamped by consultant (within Templates) - attached 8. Health and Safety Plan 9. In-charge Engineer certificate accredited by ministry of higher education 10. List of Equipment for the Laboratory 11. Scope of field and laboratory works Report Stamped by consultant 12. Valid Commercial License for laboratory
| MEPS | Traffic Study Review 8 | MEPS | Architecture Harmony Approval 9 | MEPS | Soil Investigation Work Permit 10
| 1. ITC Approved TIS 2. DoT Trip Generation 3. Circulation Plans |  | 1. Perspectives, Sun Path Diagram, Material Details, Elevations on 1 Sheet as per Template 2. Owner's and Consultant Signed and Stamped Form 3. Roofscape Policy (provided by ADM) |  | 1. Authorization and Undertaking Letter for Soil Test Permit 2. Certified Site Plan 3. Contractor Assignment Letter 4. Employee List for the Laboratory 5. ENAS accreditation certificate from Emirates Authority For Standardization and Metrology 6. Final Demarcation 7. General layout indicating borehole locations and coordinates stamped by consultant (within Templates) - attached 8. Health and Safety Plan 9. In-charge Engineer certificate accredited by ministry of higher education 10. List of Equipment for the Laboratory 11. Scope of field and laboratory works Report Stamped by consultant 12. Valid Commercial License for laboratory
| MEPS | Circulation Plan Approval 11 | MEPS | Concept Design (Preliminary Approval) 12 | MEPS | Parking Exit and Entry 13
| 1. Trip Generation and Parking Calculation Sheets 2. DoT GIS 3. Circulation Plans |  | 1. Affection Plan / Site Plan 2. Architectural Drawings (DWF): 2.1 Documents Sheets. 2.2 Drawings list & perspectives. 2.3 DCR Compliance sheet (Plot DCR, Site Plan, Villa section, Area summary table). 2.4 Area calculations sheet. 2.5 Site Setting Layout sheet. 2.6 Floor plans. 2.7 Elevations & Elev details. 2.8 Sections & sectional details. 2.9 Stair details. 2.10 Service blocks details (Plans, Elev., Sections,..etc.) 2.11 Swimming Pool Details (Plans, Elev., Sections,..etc.) 2.12 Boundary wall Details ( Plans, Elev., Sections, ...etc.) 2.13 Estidatama Documents sheet. 2.14 Code Analysis Compliance sheet (Ch1,3,4,5,6) 2.15 Code Analysis Compliance sheet (Ch7,8,9,10) 2.16 Code Analysis Compliance sheet (Ch10,12,24,31) |  | 1. Entrance Drawings (access) 2. External Parking Drawings
Schematic Stage | ADDC | Load Demand Notification - Electrical 14 | MEPS | Electrical Drawings Approval 15 | MEPS | Estidama Approval (if required) 16
| 1. Affection Plan 2. Consultant Appointment Letter 3. ADDC LDN Form 5. Site Setting Layout (PDF) |  | 1. Affection Plan 2. Consultant Appointment Letter 3. ADDC Approved LDN 5. Site Setting Layout (DWF) |  | 1. Affection Plan 2. Project Description Letter 3. Site Layout 4. Stamped Cover Letter
| MEPS | Sewerage Approval 17 | MEPS | Plumbing Drawings Approval 18 | MEPS | Etisalat Drawings Approval 19
| 1. Drainage Layout (DWF) 2. Drainage Calculations (PDF) |  | 1. Water Supply Layout - SLD (DWF) 2. Water Supply Calculations (PDF) |  | 1. Telecom Layout - SLD (DWF)
| MCC | CCTV Drawings Approval 20 | EAD | EIA Approval (if required) 21
| 1. Affection Plan 2. CCTV Layout (PDF) |  | 1. EIA Report
| MEPS | MCC Drawings Approval 22 | MEPS | Approval from the Environmental Agency 23
| 1. MCC Stamped Drawings (PDF) |  | 1. EAD Stamped Report 2. EAD NOC Letter
Detailed Stage | ADNOC | Gas Approval (by House of Expertise) 24
1. Gas Layout and Schematics
| MEPS | Civil Defense Drawings Approval 25 | MEPS | Structural Drawings Approval 26
| 1. Arch Life Safety (DWF) 2. Smoke Control (DWF) 3. Gas (DWF) 4. Fire Fighting and Fire Protection (DWF) 5. Fire Alarm and Emergency Lighting (DWF) 6. FLS Strategy Report (PDF) |  | 1. Structure Layouts (DWF) 2. Calculations (PDF) 3. Model (ETABS/SAFE/PROKON)
| MEPS | Final Architecture Drawings Approval 27
1. Affection Plan / Site Plan 2. Architectural Drawings (DWF): 2.1 Documents Sheets. 2.2 Drawings list & perspectives. 2.3 DCR Compliance sheet (Plot DCR, Site Plan, Villa section, Area summary table). 2.4 Area calculations sheet. 2.5 Site Setting Layout sheet. 2.6 Floor plans. 2.7 Elevations & Elev details. 2.8 Sections & sectional details. 2.9 Stair details. 2.10 Service blocks details (Plans, Elev., Sections,..etc.) 2.11 Swimming Pool Details (Plans, Elev., Sections,..etc.) 2.12 Boundary wall Details ( Plans, Elev., Sections, ...etc.) 2.13 Estidatama Documents sheet. 2.14 Code Analysis Compliance sheet (Ch1,3,4,5,6) 2.15 Code Analysis Compliance sheet (Ch7,8,9,10) 2.16 Code Analysis Compliance sheet (Ch10,12,24,31)
| MEPS | Building Permit 28
1. All Approved Layouts
| MEPS | Assign Contractor and Supervision Consultant 29
1. Affection Plan 2. Owner's ID/Trade License 3. Contractor Appointment Letter 4. Authorization & Undertaking Form 5. Supervision Consultant Appointment Letter
Construction Stage | Applications by Contractor as applicable
| MEPS | Civil Defense Shop Drawings Approval | MEPS | ADDC Shop Drawings Approval | MEPS | Telecom Shop Drawings Approval | MEPS | Strucure Shop Drawings Approval
| MEPS | Civil Defense Initial Inspection | MEPS | ADDC Initial Inspection | MEPS | Telecom Initial Inspection | MEPS | Structure Initial Inspection
| MEPS | Civil Defense Final Inspection | MEPS | ADDC Final Inspection | MEPS | Telecom Final Inspection | MEPS | Structure Final Inspection
| MEPS | Final Inspection
| MEPS | Building Completion Certificate
Other Approvals (As Applicable)
| UPC | Master Plan Concept Approval | IDAS | Infrastructure Approvals
| DoT | Department of Transport Approval
| UPC | Master Plan Final Approval

## AAM
Al Ain Municipality Process and Requirements
Pre-Concept Stage | SmartHub | Plot Setting Out Study 1 | MEPS | Project Registration 2
| 1. Affection Plan 2. Owner's ID/Trade License 3. Consultant Appointment Letter 4. Authorization & Undertaking Form |  | 1. Affection Plan 2. Owner's ID/Trade License 3. Consultant Appointment Letter 4. Authorization & Undertaking Form 5. Site Approval and Clearances Form 6. Project Registration Form
|  |  | MEPS | Site Approval and Clearances 3
1. Affection Plan 2. Owner's ID/Trade License 3. Consultant Appointment Letter 4. Authorization & Undertaking Form 5. Site Approval and Clearances Form 6. Project Registration Form
|  |  | ADSSC | NOI - Request for GIS Information 4
1. Affection Plan 2. Owner's ID/Trade License 3. Consultant Appointment Letter
Concept Stage | ITC | TIS (if required - applied by Specialist) 5 | AAM | Exceptions Approval (if required) 6 | MEPS | Soil Investigation Work Permit 7
| 1. Affection Plan 2. Site Traffic Generation 3. Traffic Access and Circulation Plans 4. Site Access Review 5. Public Transit and Non-Motorized Plans 5. Parkign Study 6. TIS Summary Plans |  | 1. Affection Plan 2. Architectural Drawings (PDF): 2.1 Plans, Sections, Elevations highlighting area for Exception 3. Supporting documents/drawings - as applicable |  | 1. Authorization and Undertaking Letter for Soil Test Permit 2. Certified Site Plan 3. Contractor Assignment Letter 4. Employee List for the Laboratory 5. ENAS accreditation certificate from Emirates Authority For Standardization and Metrology 6. Final Demarcation 7. General layout indicating borehole locations and coordinates stamped by consultant (within Templates) - attached 8. Health and Safety Plan 9. In-charge Engineer certificate accredited by ministry of higher education 10. List of Equipment for the Laboratory 11. Scope of field and laboratory works Report Stamped by consultant 12. Valid Commercial License for laboratory
| MEPS | Traffic Study Review 8 | MEPS | Architecture Harmony Approval 9 | MEPS | Soil Investigation Work Permit 10
| 1. ITC Approved TIS 2. DoT Trip Generation 3. Circulation Plans |  | 1. Perspectives, Sun Path Diagram, Material Details, Elevations on 1 Sheet as per Template 2. Owner's and Consultant Signed and Stamped Form 3. Roofscape Policy (provided by ADM) |  | 1. Authorization and Undertaking Letter for Soil Test Permit 2. Certified Site Plan 3. Contractor Assignment Letter 4. Employee List for the Laboratory 5. ENAS accreditation certificate from Emirates Authority For Standardization and Metrology 6. Final Demarcation 7. General layout indicating borehole locations and coordinates stamped by consultant (within Templates) - attached 8. Health and Safety Plan 9. In-charge Engineer certificate accredited by ministry of higher education 10. List of Equipment for the Laboratory 11. Scope of field and laboratory works Report Stamped by consultant 12. Valid Commercial License for laboratory
| MEPS | Circulation Plan Approval 11 | MEPS | Concept Design 12 | MEPS | Parking Exit and Entry 13
| 1. Trip Generation and Parking Calculation Sheets 2. DoT GIS 3. Circulation Plans |  | 1. Affection Plan 2. Architectural Drawings (DWF): 2.1 Cover Sheet 2.2 Project Documents Sheet 2.3 Drawings Schedule 2.4.Area Calculation Sheet 2.5 Site Setting Layout 2.6 Floor Plans 2.7 Elevations 2.8 Sections 2.9 Perspectives |  | 1. Entrance Drawings (access) 2. External Parking Drawings
Schematic Stage | ADDC | Load Demand Notification - Electrical 14 | MEPS | Electrical Drawings Approval 15 | MEPS | Estidama Approval (if required) 16
| 1. Affection Plan 2. Consultant Appointment Letter 3. ADDC LDN Form 5. Site Setting Layout (PDF) |  | 1. Affection Plan 2. Consultant Appointment Letter 3. ADDC Approved LDN 5. Site Setting Layout (DWF) |  | 1. Affection Plan 2. Project Description Letter 3. Site Layout 4. Stamped Cover Letter
| MEPS | Sewerage Approval 17 | MEPS | Plumbing Drawings Approval 18 | MEPS | Etisalat Drawings Approval 19
| 1. Drainage Layout (DWF) 2. Drainage Calculations (PDF) |  | 1. Water Supply Layout - SLD (DWF) 2. Water Supply Calculations (PDF) |  | 1. Telecom Layout - SLD (DWF)
| MCC | CCTV Drawings Approval 20 | EAD | EIA Approval (if required) 21
| 1. Affection Plan 2. CCTV Layout (PDF) |  | 1. EIA Report
| MEPS | MCC Drawings Approval 22 | MEPS | Approval from the Environmental Agency 23
| 1. MCC Stamped Drawings (PDF) |  | 1. EAD Stamped Report 2. EAD NOC Letter
Detailed Stage | ADNOC | Gas Approval (by House of Expertise) 24
1. Gas Layout and Schematics
| MEPS | Civil Defense Drawings Approval 25 | MEPS | Structural Drawings Approval 26
| 1. Arch Life Safety (DWF) 2. Smoke Control (DWF) 3. Gas (DWF) 4. Fire Fighting and Fire Protection (DWF) 5. Fire Alarm and Emergency Lighting (DWF) 6. FLS Strategy Report (PDF) |  | 1. Structure Layouts (DWF) 2. Calculations (PDF) 3. Model (ETABS/SAFE/PROKON)
| MEPS | Final Architecture Drawings Approval 27
1. Affection Plan 2. Architectural Drawings (DWF): 2.1 Cover Sheet 2.2 Drawings Schedule 2.3 Project Document Sheet 2.4.Area Calculation Sheet 2.5 Site Setting Layout 2.6 Floor Plans 2.7 Elevations 2.8 Sections 2.9 Perspectives 2.10 Wall Types, Sections & Details 2.11 Cladding Details 2.12 Stair Details 2.13 Lift Details 2.14 Door and Window Schedules 2.15 Boundary Wall Details 2.16 Wet Area Details 2.17 Service Room Details 2.18 Ramp Details 2.19 Accessibility Routes 2.20 Finishes Details
| MEPS | Building Permit 28
1. All Approved Layouts
| MEPS | Assign Contractor and Supervision Consultant 29
1. Affection Plan 2. Owner's ID/Trade License 3. Contractor Appointment Letter 4. Authorization & Undertaking Form 5. Supervision Consultant Appointment Letter
Construction Stage | Applications by Contractor as applicable
| MEPS | Civil Defense Shop Drawings Approval | MEPS | ADDC Shop Drawings Approval | MEPS | Telecom Shop Drawings Approval | MEPS | Strucure Shop Drawings Approval
| MEPS | Civil Defense Initial Inspection | MEPS | ADDC Initial Inspection | MEPS | Telecom Initial Inspection | MEPS | Structure Initial Inspection
| MEPS | Civil Defense Final Inspection | MEPS | ADDC Final Inspection | MEPS | Telecom Final Inspection | MEPS | Structure Final Inspection
| MEPS | Final Inspection
| MEPS | Building Completion Certificate
Other Approvals (As Applicable)
| UPC | Master Plan Concept Approval | IDAS | Infrastructure Approvals
| DoT | Department of Transport Approval
| UPC | Master Plan Final Approval

## SM
Sharjah Municipality Process and Requirements
Pre-Concept Stage | SDTPS | Affection Plan & Planning Conditions Statement 1
1. Owner's ID/Trade License 2. Consultant Appointment Letter 3. Consultant Trade License
| SDTPS | Plot Demarcation Study 2 | SEWA | Information NOC
| 1. Affection Plan 2. Owner's ID/Trade License 3. Consultant Appointment Letter |  | 1. Affection Plan 2. Application Form 3. Consultant Appointment Letter 4. Cover Letter
Concept Stage | SDTPS | Initial Designs Approval 4
1. Affection Plan 2. Owner's ID/Trade License 3. Consultant Appointment Letter addressed to SDTPS 4. Consultant Trade License 5. Planning Condition Statement 6. Arch Drawings (DWF) 6.1 Cover Sheet 6.2 Project Documents Sheet 6.3 Drawings Schedule 6.4.Area Calculation Sheet 6.5 Site Setting Layout 6.6 Floor Plans 6.7 Elevations 6.8 Sections 6.9 Perspectives
Schematic Stage | SEWA | Electrical Approval 5 | SEWA | Water Approval 6 | SEWA | Natural Gas Approval 7
| 1. Lighting Layout (CAD)​ 2. Power Layout (CAD)​ 3. Schematic Schedule (CAD)​ 4. Architectural Layout (CAD)​ 5. SEWA Form (with Consultant Appointment Letter, Project Desription Letter, Affection Plan, AAE Trade License, SEWA Card) |  | 1. Water Supply Layout (CAD)​ 2. Architectural Layout (CAD)​ 3. Consultant Undertaking for Fire Pump Room ​ 4. Owner's Undertaking for Fire Pump Room​ 5. SEWA Form (with Consultant Appointment Letter, Project Desription Letter, Affection Plan, AAE Trade License, SEWA Card) |  | 1. Natural Gas Layout (CAD)​ 2. Architectural Layout (CAD)​ 3. SEWA Form (with Consultant Appointment Letter, Project Desription Letter, Affection Plan, AAE Trade License, SEWA Card)​
| MOI-SCD | Civil Defense Approval 8 | SM | Drainage Approval 9 | Etisalat | Telecom NOC - Etisalat 10 | SRTA | Access Approval (if required) 11
| 1. Architecture Life Safety (PDF)- (Occupancies, Window & Door Schedules, Sections, Plans, Site Setting Layout)​ 2. Fire Alarm and Emergency Lighting (PDF)​ 3. Fire Protection and Smoke Management (PDF)​ 4. Letter from Owner​ 4. Project description Letter​ 5. Owner's Emirates ID​ 6. Affection Plan |  | 1. Affection Plan​ 2. Consultant Appointment Letter​ 3. AAE Trade License ​ 4. Cover Letter​ 5. Site Setting Layout (CAD)​ 6. Drainage Layout (CAD) |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. Telecom Layout (DWF) |  | 1. Affection Plan 2. Site Setting Layout (PDF) 3. Access Drawing (PDF)
Detailed Stage | SM | Engineering Drawings Approval 12
1. Affection Plan​ 2. Title Deed (with Municiaplity Stamp)​ 3. AAE Trade License​ 4. Consultant Appointment Letter​ 5. Soil Investigation Report​ 6. Architecture Drawings (DWF)​ 7. Structure Drawings (DWF)​ 8. Approval from Drainage Department​ 9. Approval from SEWA (E,G,W)​ 10. Approval from Civil Defense ​ 11. Approval from DTPS
| SM | Masaar 13
1. Plot Number​ 2. Engineering Drawings Approval Application Number
Construction Stage | SM | Building Permit 14
1. Building Permit Application Form​ 2. Stamped Drawings and Approval Certificate from SM​ 3. AAE Trade License​ 4. Trade License of Contractor​ 5. Appointment Letter/Contract between Owner and Contractor (indicating contract amount)​ 6. Undertaking Letter from Consultant (responsibility of supervision and thermal insulation works as per SM Standards)​ 7. SM Drainage NOC (Construction NOC)​ 8. Etisalat NOC (Construction NOC)​ 9. SEWA Water NOC (Construction NOC)​ 10. SEWA Electricity NOC (Construction NOC)​ 11. SEWA Gas NOS NOC (Construction NOC)​ 12. Affection Plan (renewed)​ 13. Title Deed (renewed stamp)​ 14. Sharjah Civil Defence Approval ​ 15. Project Specs (signed by client, signed and stamped by AAE and Contractor)​ 16. Undertaking Letter from Consultant (responsibility of lift works according to standards)​ 17. Receipt of SM Drawings Approval​ 18. Approval of DTPS (first page only)​ 19. Electricity Connection Date (first page of SEWA Elec. Approved drawings)​ 20.Insurance Receipt (once all above are submitted via email, link will be sent for contractor to make payment, and receipt will be sent back to SM with all the above again​
Applications by Contractor as applicable
| SEWA | Electrical Shop Drawings Approval | SEWA | Water Shop Drawings Approval | SEWA | Natural Gas Shop Drawings Approval | SM | Drainage Shop Drawings Approval
| SRTA | Site Access Approval
Residential
Commercial / other Facilities
Industrial

## MOI - SCD
Sharjah Civil Defense Process and Requirements
Schematic Stage | SCD | Civil Defense Approval
1. Architecture Life Safety (PDF)- (Occupancies, Window & Door Schedules, Sections, Plans, Site Setting Layout)​ 2. Fire Alarm and Emergency Lighting (PDF)​ 3. Fire Protection and Smoke Management (PDF)​ 4. Letter from Owner​ 4. Project description Letter​ 5. Owner's Emirates ID​ 6. Affection Plan
Construction Stage | SCD | Modification Approval (as required)
As Approved As Revised Drawings (Clouded PDF) - as applicable: 1. Architecture Life Safety (PDF)- (Occupancies, Window & Door Schedules, Sections, Plans, Site Setting Layout)​ 2. Fire Alarm and Emergency Lighting (PDF)​ 3. Fire Protection and Smoke Management (PDF)​ 4. Letter from Owner​ 4. Project description Letter​ 5. Owner's Emirates ID​ 6. Affection Plan
Completion Stage | SCD | Building Completion Inspection Request | Not Included as the stage is not a valid one
1. Letter from Consultant stating that all installed equipments in the building are reasy for inspection 2. Location Site Map and Water Map 3. Trade Licenses of the Alarm and Fire Fighting System Suppliers 4. Letter from Suppliers stating that they are ready for inspection 5. Pledge by applicant that all the materials used are matchign with the requirements of the UAE Code 6. List of Installed items, with supplier details and equipment brand names

## SDTPS
Sharjah Municipality Process and Requirements
Pre-Concept Stage | SDTPS | Affection Plan & Planning Conditions Statement 1
1. Owner's ID/Trade License 2. Consultant Appointment Letter 3. Consultant Trade License
| SDTPS | Plot Demarcation Study 2 | SEWA | Information NOC 3
| 1. Affection Plan 2. Owner's ID/Trade License 3. Consultant Appointment Letter |  | 1. Affection Plan 2. Application Form 3. Consultant Appointment Letter 4. Cover Letter
Concept Stage | SDTPS | Initial Designs Approval 4
1. Affection Plan 2. Owner's ID/Trade License 3. Consultant Appointment Letter addressed to SDTPS 4. Consultant Trade License 5. Planning Condition Statement 6. Arch Drawings (DWF) 6.1 Cover Sheet 6.2 Project Documents Sheet 6.3 Drawings Schedule 6.4.Area Calculation Sheet 6.5 Site Setting Layout 6.6 Floor Plans 6.7 Elevations 6.8 Sections 6.9 Perspectives
Schematic Stage | SEWA | Electrical Approval 5 | SEWA | Water Approval 6 | SEWA | Natural Gas Approval 7
| 1. Lighting Layout (CAD)​ 2. Power Layout (CAD)​ 3. Schematic Schedule (CAD)​ 4. Architectural Layout (CAD)​ 5. SEWA Form (with Consultant Appointment Letter, Project Desription Letter, Affection Plan, AAE Trade License, SEWA Card) |  | 1. Water Supply Layout (CAD)​ 2. Architectural Layout (CAD)​ 3. Consultant Undertaking for Fire Pump Room ​ 4. Owner's Undertaking for Fire Pump Room​ 5. SEWA Form (with Consultant Appointment Letter, Project Desription Letter, Affection Plan, AAE Trade License, SEWA Card) |  | 1. Natural Gas Layout (CAD)​ 2. Architectural Layout (CAD)​ 3. SEWA Form (with Consultant Appointment Letter, Project Desription Letter, Affection Plan, AAE Trade License, SEWA Card)​
| MOI-SCD | Civil Defense Approval 8 | SM | Drainage Approval 9 | Etisalat | Telecom NOC - Etisalat 10 | SRTA | Access Approval (if required) 11
| 1. Architecture Life Safety (PDF)- (Occupancies, Window & Door Schedules, Sections, Plans, Site Setting Layout)​ 2. Fire Alarm and Emergency Lighting (PDF)​ 3. Fire Protection and Smoke Management (PDF)​ 4. Letter from Owner​ 4. Project description Letter​ 5. Owner's Emirates ID​ 6. Affection Plan |  | 1. Affection Plan​ 2. Consultant Appointment Letter​ 3. AAE Trade License ​ 4. Cover Letter​ 5. Site Setting Layout (CAD)​ 6. Drainage Layout (CAD) |  | 1. Affection Plan 2. Site Setting Layout (DWF) 3. Telecom Layout (DWF) |  | 1. Affection Plan 2. Site Setting Layout (PDF) 3. Access Drawing (PDF)
Detailed Stage | SM | Engineering Drawings Approval 12
1. Affection Plan​ 2. Title Deed (with Municiaplity Stamp)​ 3. AAE Trade License​ 4. Consultant Appointment Letter​ 5. Soil Investigation Report​ 6. Architecture Drawings (DWF)​ 7. Structure Drawings (DWF)​ 8. Approval from Drainage Department​ 9. Approval from SEWA (E,G,W)​ 10. Approval from Civil Defense ​ 11. Approval from DTPS
| SM | Masaar 13
1. Plot Number​ 2. Engineering Drawings Approval Application Number
Construction Stage | SM | Building Permit 14
1. Building Permit Application Form​ 2. Stamped Drawings and Approval Certificate from SM​ 3. AAE Trade License​ 4. Trade License of Contractor​ 5. Appointment Letter/Contract between Owner and Contractor (indicating contract amount)​ 6. Undertaking Letter from Consultant (responsibility of supervision and thermal insulation works as per SM Standards)​ 7. SM Drainage NOC (Construction NOC)​ 8. Etisalat NOC (Construction NOC)​ 9. SEWA Water NOC (Construction NOC)​ 10. SEWA Electricity NOC (Construction NOC)​ 11. SEWA Gas NOS NOC (Construction NOC)​ 12. Affection Plan (renewed)​ 13. Title Deed (renewed stamp)​ 14. Sharjah Civil Defence Approval ​ 15. Project Specs (signed by client, signed and stamped by AAE and Contractor)​ 16. Undertaking Letter from Consultant (responsibility of lift works according to standards)​ 17. Receipt of SM Drawings Approval​ 18. Approval of DTPS (first page only)​ 19. Electricity Connection Date (first page of SEWA Elec. Approved drawings)​ 20.Insurance Receipt (once all above are submitted via email, link will be sent for contractor to make payment, and receipt will be sent back to SM with all the above again​
Applications by Contractor as applicable
| SEWA | Electrical Shop Drawings Approval | SEWA | Water Shop Drawings Approval | SEWA | Natural Gas Shop Drawings Approval | SM | Drainage Shop Drawings Approval
| SRTA | Site Access Approval

## SHARJAH
CITY | AUTHORUTY | Submission Type |  | Project Type | Project | Prerequisites | If Initial Permit is available | Project Status | Fees Calculation Details
| AUTHORUTY | Submission Name in General | Submission Name as per Authority | Project Type | Project | Prerequisites | If Initial Permit is available | Project Status | Proposed | Existing
SHARJAH | SDTPS | Affection Plan & Planning Conditions Statement
Plot Demarcation Study
|  | Concept Design Approval | Approve Initial Designs | Commercial/Other Facilities | New | 1. Affection Plan 2. Owner's ID/Trade License 2.1. Individuals – EID 2.2. Private Company – Trade license 2.3. Government - EID 2.4. GCC Investor - ID 2.5. Non-Resident Investor - ID 3. Consultant Appointment Letter addressed to SDTPS 4. Consultant Trade License 5. Planning Condition Statement 6. Arch Drawings (DWF) 6.1 Cover Sheet 6.2 Project Documents Sheet 6.3 Drawings Schedule 6.4.Area Calculation Sheet 6.5 Site Setting Layout 6.6 Floor Plans 6.7 Elevations 6.8 Sections 6.9 Perspectives |  | 1. Proposed | To be separated as floor/service | -
[5 empty] | Modification | 1. Affection Plan 2. Owner's ID/Trade License 2.1. Individuals – EID 2.2. Private Company – Trade license 2.3. Government - EID 2.4. GCC Investor - ID 2.5. Non-Resident Investor - ID 3. Consultant Appointment Letter addressed to SDTPS 4. Consultant Trade License 5. Planning Condition Statement 6. Building Permit 7. All previous design approvals 8. Arch Drawings (DWF) 8.1 Cover Sheet 8.2 Project Documents Sheet 8.3 Drawings Schedule 8.4.Area Calculation Sheet 8.5 Site Setting Layout 8.6 Floor Plans 8.7 Elevations 8.8 Sections 8.9 Perspectives | If apply with initial permit the below is required: 1. SEWA case id 2. SEWA premise id 3. SEWA account id 4. Number of rooms proposed 5. Nationality | 1. Existing 2. Under Construction | To be separated as floor/service | To be separated as floor/service
|  |  |  | Residential | New | 1. Affection Plan 2. Owner's ID/Trade License 2.1. Individuals – EID 2.2. Private Company – Trade license 2.3. Government - EID 2.4. GCC Investor - ID 2.5. Non-Resident Investor - ID 3. Consultant Appointment Letter addressed to SDTPS 4. Consultant Trade License 5. Planning Condition Statement 6. Arch Drawings (DWF) 6.1 Cover Sheet 6.2 Project Documents Sheet 6.3 Drawings Schedule 6.4.Area Calculation Sheet 6.5 Site Setting Layout 6.6 Floor Plans 6.7 Elevations 6.8 Sections 6.9 Perspectives 7. Download Service form from Submission window and to be filled |  | 1. Proposed | To be separated as floor/service | -
[5 empty] | Modification | 1. Affection Plan 2. Owner's ID/Trade License 2.1. Individuals – EID 2.2. Private Company – Trade license 2.3. Government - EID 2.4. GCC Investor - ID 2.5. Non-Resident Investor - ID 3. Consultant Appointment Letter addressed to SDTPS 4. Consultant Trade License 5. Planning Condition Statement 6. Building Permit 7. All previous design approvals 8. Arch Drawings (DWF) 8.1 Cover Sheet 8.2 Project Documents Sheet 8.3 Drawings Schedule 8.4.Area Calculation Sheet 8.5 Site Setting Layout 8.6 Floor Plans 8.7 Elevations 8.8 Sections 8.9 Perspectives 9. Download Service form from Submission window and to be filled | If apply with initial permit the below is required: 1. SEWA case id 2. SEWA premise id 3. SEWA account id 4. Number of rooms proposed 5. Nationality | 1. Existing 2. Under Construction | To be separated as floor/service | To be separated as floor/service
|  |  |  | Industrial | New | 1. Affection Plan 2. Owner's ID/Trade License 2.1. Individuals – EID 2.2. Private Company – Trade license 2.3. Government - EID 2.4. GCC Investor - ID 2.5. Non-Resident Investor - ID 3. Consultant Appointment Letter addressed to SDTPS 4. Consultant Trade License 5. Planning Condition Statement 6. Arch Drawings (DWF) 6.1 Cover Sheet 6.2 Project Documents Sheet 6.3 Drawings Schedule 6.4.Area Calculation Sheet 6.5 Site Setting Layout 6.6 Floor Plans 6.7 Elevations 6.8 Sections 6.9 Perspectives 7. Download Service form from Submission window and to be filled |  | 1. Proposed | To be separated as floor/service | -
[5 empty] | Modification | 1. Affection Plan 2. Owner's ID/Trade License 2.1. Individuals – EID 2.2. Private Company – Trade license 2.3. Government - EID 2.4. GCC Investor - ID 2.5. Non-Resident Investor - ID 3. Consultant Appointment Letter addressed to SDTPS 4. Consultant Trade License 5. Planning Condition Statement 6. Building Permit 7. All previous design approvals 8. Arch Drawings (DWF) 8.1 Cover Sheet 8.2 Project Documents Sheet 8.3 Drawings Schedule 8.4.Area Calculation Sheet 8.5 Site Setting Layout 8.6 Floor Plans 8.7 Elevations 8.8 Sections 8.9 Perspectives 9. Download Service form from Submission window and to be filled | If apply with initial permit the below is required: 1. SEWA case id 2. SEWA premise id 3. SEWA account id 4. Number of rooms proposed 5. Nationality | 1. Existing 2. Under Construction | To be separated as floor/service | To be separated as floor/service